## Instructions
Purpose of Benefit Register
The purpose of a program or project is to deliver change in an organized, planned structure. For change to be effective, benefit(s) must be identified, managed, and realized for the deliverable(s) and change(s) to be justified and accepted. The benefit register is an up to date list of planned benefits, who is responsible for measuring them, when they are expected to be realized, how they will be measured, baseline and current measurements, et cetera. The benefits in the register should encompass the reason for doing the program/project and justify the time and expense of making the change. Realization of the benefits listed in the register form a critical aspect of measuring program/project success.
Benefit Register Participants and Audience
Input into the benefit register may come from many different sources including, but not limited to, Sponsor, senior leadership, program/project intake form and/or business case, organizational and/or business unit strategic plans and initiatives, existing documentation, subject matter experts within business unit(s), and other stakeholders (such as staff, students, faculty).
The author and maintainer is the Program/Project Manager. Changes to benefits should be authorized through a formal Change Request by the Sponsor.
Instructions
1. Research and understand program/project information by reading any prior documentation (such as intake form(s), business case(s), and research/analysis) and speaking to Sponsor and other stakeholders. Identify why the program/project is being approved, what the expectations are for the final results, and what would make the deliverable(s) successful in the eyes of the sponsor and other stakeholders. These types of questions will help identify the benefits, which will sometimes be tied to business strategies/goals/objectives. Benefits, whether tangible or intangible, must be measurable.
2. Enter benefits in the benefit register with input from applicable stakeholders and Sponsor by filling out the applicable sections in the spreadsheet. The green italic text provides an example of a benefit and may be removed. See the Definitions page for a further description of each column on the spreadsheet, as well as valid values.
3. Update the document, as required, to reflect approved benefit changes as the program/project evolves.
4. Execute benefit measurements as outlined in register, recording actual results appropriately.
5. Upload to the Knowledge Base
Next Steps
Execute and document the benefit measurements according to the information laid out in this document. Update this document to reflect any approved changes during program/project execution. Monitor this register throughout execution to ensure that the program/project remains on track to deliver the expected benefits. Reflect final measurements in this document at the end of the program/project and use this document during program/project closure to assess program success.

## Benefits Register
Benefit ID | Benefit Title and Description | Requestor | State | Link to Objectives (Project, Business, Strategic) | Owner | Planned Outcome | Stakeholders and Beneficiaries | Program/Project ID and/or Name | Measure Description & Expected Result | Baseline Measure | Measure Frequency | Actual Measures | Status | Expected Realization Date | Actual Realization Date
MCP_BEN_01 | Retain warfighting capabilities | Forces Command (FORSCOM) G6 - Mission Command | Active | Strategic Objective 2.6 - Increase resiliency of Command, Control, and Communications (C3) capabilities | CPT G | All necessary warfighting capabilities required have representation and are fully mission capable upon MCP establishment | Commanders, Operations, Administration, Intelligence, Communications, Logistics | Large Scale Combat Operations (LSCO) Main Command Post (MCP) | Division Network Operations Center (DNOC) catalogues all used systems during exercise; Expected result: varied based on Brigade Commander's approved PACE Communications plan | Suite of Army Battle Command Systems (ABCS) - CPOF, AFATDS, AMDWS, MCS, BCS3, ASAS, FBCB2, TAIS, GCCS-A, DCGS, DTSS, IMETS, CPCE | Monthly during project, annually after approved design |  | On Track | 2024-10-01
MCP_BEN_02 | Reduce Electronic Warfare (EW) threat | FORSCOM G3 - Operations | Active | Strategic Objective 2.1 - Shape a 21st cenury defense industrial base --> Perforamnce Goal 2.1.2 - Optimize the organic and commercial manufacturing and repair continuum | CPT G | EW Team Mesurement of EM signature is reduced by half by project completion. | Total Force - Light Infantry Battalions | LSCO MCP | EW team measures EM signature of each MCP four times (Comms window open, Comms window closed, Emission Control measure, and while in conflict); varied based on Brigade Commander's approved PACE Communications plan | EM signature from Infantry Battalion Tactical Operations Center from COIN operations | Four measures each month during project, as requested after approved design |  | On Track | 2024-10-01
MCP_BEN_03 | Flexible and modularity to fit needs of Commander | FORSCOM G6 - Mission Command | Active | Project Objective 1.1 - Enhance flexibility and modularity of MCP design | CPT G | MCP layout and design is reduced to a 40 foot diameter by project completion | Commanders, Operations, Administration, Intelligence, Communications, Logistics | LSCO MCP | Size measured in feet and layout design overlay; expected result is reduced footprint as testing occurs | Unit's current TOC configuration | Monthly during project, annually after approved design |  | On Track | 2024-10-01
MCP_BEN_04 | Redundant capabilities | FORSCOM G6 - Mission Command | Active | Strategic Objective 2.6 - Increase resiliency of Command, Control, and Communications (C3) capabilities | CPT G | Each warfighting function has at least two means of information visualization and two means of transporting digital products by project completion | Commanders, Operations, Administration, Intelligence, Communications, Logistics | LSCO MCP | Digital and analog capabilities are catalogued and communicated through signal assets measured by DNOC and project team members; expected result is no diminished returns of warfighting functions | The Warfighting Functions of Logistics, Manuever, Mission Command, Protection, Intelligence, Operations, Fires, and Sustainment capabilities are catalogued | Monthly during project, annually after approved design |  | On Track | 2024-10-01
MCP_BEN_05 | Doctrine change for Light Infantry | Training and Docrtrine (TRADOC) G3 - Operations | Future | Strategic Objective 3.1 - Grow our talent to shape an appropriately skilled, resilient, and ready future workforce --> Performance Goal 3.1.3 - Shape training and education for emerging skillsets | CPT G | New LSCO MCP doctrine published superceeding previous Command Post Doctrine by six months after project completion | Total Force - Light Infantry Battalions | LSCO MCP | Army Publishing Directorate publishes update Command Post Doctrine based on LSCO lessons learned; likely outdated by time of publication, control measures and countermeasures developed and implemented faster than oversight committee doctrine approval process | Current Published Doctrine | Annually after approved design |  | On Track | 2025-04-01
MCP_BEN_06 | Circumvent acquistions process | FORSCOM G8 - Finance | Active | Strategic Objective 4.4 - Foster a high integrity funds control environment --> Performance Goal 4.4.1 - Increase control over our enacted budget execution by developing spend plans using a standard methodology | CPT G | Existing approved budget adhered to by creative means of acquisitions throughout project window of one year | Commanders, Finance, and Logistics | LSCO MCP | Measure is the approved budget for Fiscal Year 2024; once congress passes budget, expected result is repurposing previously purchased materials to complete project | Current approved budget | Annually, fiscal year begins 01OCT |  | On Track | 2024-01-01
MCP_BEN_07 | Increase efficiency of displacement and establishment | FORSCOM G3 - Operations | Active | Project Objective 1.2 - Reduce Non-Mission capable time | CPT G | Reduce establishment time for Intermediate Operationally Capable (IOC) to five minutes once at new site and for Fully Operationally Capable (FOC) to one hour once at new site. Reduce displacement time of FOC MCP to initiating movement to one hour by project completion | Total Force - Light Infantry Battalions | LSCO MCP | Each time the Battalion MCP is moving during exercise, the project team will capture set-up / tear-down times; expected result is a reduction to less than one hour establishment or displacement | ATP 6-0.5 states a BN MCP needs to be established or displaced within two hours | Four measures each month during project, as requested after approved design |  | On Track | 2024-10-01
MCP_BEN_08 | Practical "How-to" guide products | TRADOC G6 - Mission Command | Future | Strategic Objective 3.1 - Grow our talent to shape an appropriately skilled, resilient, and ready future workforce --> Performance Goal 3.1.3 - Shape training and education for emerging skillsets | CPT G | Digital document less than 20 pages of LSCO MCP layout and design features published and available on Army Publishing Directorate by project completion | Total Force - Light Infantry Battalions | LSCO MCP | Comprehensive and digestable guides on LSCO MCP establishment; expected result is publication on time | "How-to" guide products for TOCs | Once upong project completion, annually after approved design |  | On Track | 2024-10-01
Note on A1: Salonen, Deb: Sequential numbering in the format BEN-###.
Note on B1: Salonen, Deb: A description of the desired benefit, including a title, current and target state/measurement
Note on C1: Salonen, Deb: The individual that raised the benefit for inclusion as part of the Program.
Note on D1: Salonen, Deb: hat state is the benefit o Active o Future
Note on E1: Salonen, Deb: Document which University or IT Strategy/Strategies this benefit aligns to, and how
Note on F1: Salonen, Deb: The individual responsible for measuring benefit progress, and accomplishing the benefit objective.
Note on G1: Salonen, Deb: What changes will take place, and what will the results look like, in order to achieve the benefit (“Benefit Vision”)
Note on H1: Salonen, Deb: Individuals or groups who will be impacted by and/or benefit from the Planned Outcome.
Note on I1: Salonen, Deb: The ID (from the Portfolio list) and name of the project(s) or initiative(s) within the Program that will deliver the Planned Outcome.
Note on J1: Salonen, Deb: What measurement will be used to gauge progress and success in achieving the benefit? What value is required to be deemed a success?
Note on K1: Salonen, Deb: What was the value of the measure before work started?
Note on L1: Salonen, Deb: How often will a progress measurement take place?
Note on M1: Salonen, Deb: What was the latest progress measurement?
Note on N1: Salonen, Deb: High level status of the progress achieved to date, based on progress measurement versus elapsed time, to deliver the Planned Outcome. o On Track = On Schedule, Budget and Scope o Warning = Significant risk to Schedule, Budget and/or Scope o Critical = Schedule, Budget and/or Scope will not be met o Realized = Benefit realized o NOT Realized = Decision made that benefit will not be realized

## Definitions & Values
Benefit Register Definitions and Values
Benefit ID – A unique identifer or number for each benefit entered | Measure Description & Expected Result – What measurement will be used to gauge progress and success in achieving the benefit? What value is required to be deemed a success?
Benefit Title and Description – A title and brief description of the desired benefit | Baseline Measure – What was the value of the measure before work started?
Requestor – The individual or stakeholder group that raised the benefit for inclusion. | Measure Frequency – How often will a progress measurement take place?
State - State of current benefit. o Active = Benefit is currently active o Future = Benefit is identified for the future | Actual Measures – What are the actual measurement results and the date taken?
Link to Business Objectives – Document or link to University, departmental, or IT strategies this benefit aligns to, and how | Status – High level status of the progress achieved to date, based on progress measurement versus elapsed time, to deliver the Planned Outcome. o Realized = Benefit has been realized. Actual result matches expected. o On Track = On Schedule for realizing benefit. o Warning = Some risk towards realizing benefit. o Critical = Benefit realization will not be met.
Owner – The individual responsible for measuring benefit progress, and accomplishing the benefit objective. | Expected Realization Date – Year and month originally planned for completion of Planned Outcome.
Planned Outcome – What changes will take place, and what will the results look like, in order to achieve the benefit (“Benefit Vision”) | Actual Realization Date – Date of completion of the Planned Outcome/Benefit. If the full benefit is no longer expected, enter N/A
Stakeholders and Beneficiaries – Individuals or groups who will be impacted by and/or benefit from the Planned Outcome.
Program/Project ID and Name – The ID and/or name of the program, project(s), or initiative(s) that will deliver the Planned Outcome

## Sheet1 (hidden)
Active
Future
Realized
On Track
Warning
Critical