## Weekly Gantt Chart Template
LSCO MCP WEEKLY GANTT CHART
| Project: |  | Large Scale Combat Operations Main Command Post
| Project Manager: |  | CPT G
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
WEEK
Task name | Progress | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86
Staff / Team Appointments | 60%
Contracts and Agreements Finalized | 40%
Near-Peer Competitor MCP Analysis | 20%
Russo-Ukraine Conflict Lessons Learned | 15%
Preliminary Design | 35%
Concept Sketches | 60%
Initial Design Complete | 0%
Prototype Materials Acquired | 0%
Materials Ordered | 0%
Materials Delivered | 0%
Initial Prototype Constructed | 0%
MCP Layout Prototypes Tested | 0%
2IBCT / 82D ABN DIV | 0%
3IBCT / 25TH IN DIV | 0%
75TH RANGER REG | 0%
2IBCT / 101ST ABN DIV | 0%
1IBCT / 11TH ABN DIV | 0%
1IBCT / 82D ABN DIV | 0%
7TH SF GROUP | 0%
1IBCT / 10TH MTN DIV | 0%
Aerial Image Capture | 0%
EM Emissions Data Capture | 0%
Stakeholder Touchpoints | 0%
Project Status Presentation | 0%
Prototype Design Refinement | 0%
Concept Sketches | 0%
Design Complete | 0%
Revised Prototype Constructed | 0%
FORSCOM Visit | 0%
Project Status Presentation | 0%
Layout and Design Final Plans | 0%
Final Data Compilation | 0%
Results Summary | 0%
Writing / Document Creation | 0%
Proofreading / Quality Control | 0%
FORSCOM Approval | 0%
Results Published | 0%
Writing / Document Creation | 0%
Proofreading / Quality Control | 0%
Army Training Publication | 0%