## Master Data
Assumptions & Constraints Log
Project: | Large Scale Combat Operations Main Command Post (LSCO MCP)
Project Manager: | CPT G
Document Owner: | Knowledge Manager
Document Creation Date: | 2023-10-28
Last Document Change Date: | 2023-10-29
Last changed by: | CPT G
Confidentiality level: | Unclassified
Authorized to read: | Project Team, Rotational Brigades, FORSCOM, Chain of Command
Authorized to change (besides the document owner): | Project Manager, Military Liaison
Versioning scheme: | v2
Review frequency of document: | Monthly
Master document storage place: | Project Team MS Teams
Approval for new version needed (name): | JRTC Commander
Publication procedure for new document version: | Project Team MS Teams

## Document Guide
Guide to the Assumptions & Constraints Log
1. Take key decisions on document management & update sheet "Master Data" accordingly - What is the confidentiality level of the document? Who is authorized to read the document? Does the document have to be password-protected? - Who will be the document owner? Who is authorized to update the document apart from the document owner (if any)? - What is the planned frequency of document reviews & updates? - Where will the document be stored? - How will versions be marked (date in file name or version number in file name or...)? - Do new document versions have to be approved before publication? If yes, by whom? - How will new versions of the document be published and the stakeholder community be informed about a new version?
2. Take decisions on master data for this document & update tab "Ranges" accordingly! - What assumption/constraint status do you want to use in managing the assumptions and constraints? - What categories do you want to use for the assumptions and constraints?
3. Decide if you want to use the simple or advanced version of the assumptions & constraints sheet! - If in doubt start with the simple version. You can change later easily to the advanced version via copy & paste if there is a compelling reason to use the additional columns. Especially at project start the focus should be on managing the constraints and assumptions and not on managing the document! Start simple and stay simple as long as possible!
4. Remove example data from simple or advanced version of the assumptions & constraints sheet!
5. Start populating the simple or advanced sheet: - ID ==> mandatory ==> used to identify an item in the list, but you can use your own ID scheme. To start simple you can count up from one. - type ==> mandatory (valuerange) ==> defines if the item is an assumption or constraint - assumption/constraint ==> mandatory ==> describes the assumption/constraint with a few words (long form description should go into the description field) - status ==> mandatory (value range) ==> should indicate the status of the item (not verified yet/verified as correct/verified as incorrect/...) - category (only in advanced sheet) ==> optional (value range) ==> categorization of assumption/constraint (technical area/project phase/PM area/...) - description ==> optional, but recommended ==> extended description of the item (only in simple sheet: should mention documents and artifacts which are related to the assumption/constraint and might have to be reviewed and updated if there is a change to the assumption/constraint and especially if an assumption has been verified as incorrect!) - related documents & artifacts (only in advanced sheet) ==> optional ==> list of all documents and artifacts that are related to this assumption/constraint and need to be reviewed and updated if there is a change to the assumption/constraint (be as specific as possible, use hyperlinks if possible) - Comments ==> optional ==> any additional information regarding the item, which is not a description - review frequency (only in advanced sheet) ==> optional ==> state if there is a review frequency planned for this particular item which is different than the review frequency of the whole document (weekly/bi-weekly/monthly/quarterly/...) - last review date (only in advanced sheet) ==> optional ==> date of last review if the status and content of the item is still up to date (even if there is no change) - Changed by (only in advanced sheet) ==> optional ==> date of the last change to this item (no matter what of the fields was change) - Change date (only in advanced sheet) ==> optional ==> person who did the last change of this item - Created by (only in advanced sheet) ==> optional ==> date when this item was added to the list initially - Creation date (only in advanced sheet) ==> optional ==> person who created this item
6. Review and update list as stated in the review cycle stated on the master data sheet (or in the column review frequency if you use the advanced sheet)! - Especially if you change an assumption status to "verified as incorrect" you should review the related documents and artifacts accordingly to reflect this. - If you verify an assumption as incorrect or add a constraint which have no effect at all on any document or artifact then that assumption and artifact is actually obsolete.

## Assumptions & Constraints
ID | Type | Assumption/Constraint | Status | Category | Description | Related Docs & Elements | Comments | Review Frequency | Last Review Date | Changed By | Change Date | Created By | Creation Date
1 | Assumption | Scope is accepted by 02OCT23 Suspense | Verified As Correct | Administrative Coordination | Project Manager and Stakeholder Approval Authority have completed and agreed upon Scope Statement NLT 02OCT23 | SOW, Milestone Chart | The Scope Statement must be agreed upon prior to project initiation | Monthly |  |  |  | CPT G | 2023-10-29
2 | Assumption | Contracts are accepted by 02OCT23 Suspense | Verified As Correct | Administrative Coordination | Project Manager and Stakeholder Approval Authority have completed and signed Contracts for Team Members and Subcontractors NLT 02OCT23 | SOW, WBS, Milestone Chart | The Contracts must be agreed upon prior to project initiation | Monthly |  |  |  | CPT G | 2023-10-29
3 | Assumption | Prototype design is approved prior to materials order processed | Verification In Process | Design | Designer has gained approval of completed schematics fulfilling requirements and completed materials list | SOW, WBS | Materials list distributed to Project Team for acquistion | Monthly |  |  |  | CPT G | 2023-10-29
4 | Assumption | Materials are available and arrive on schedule | Not Verified Yet | Material Acquisition | Utulizing the Army's class of supply system, GCSS-A, materials are procured and delivered on schedule | WBS, Milestone Chart | Administrators require GCSS-A access and SLOC of local SSA | Monthly |  |  |  | CPT G | 2023-10-29
5 | Assumption | Approved budget covers projected and unforeseen costs | Not Verified Yet | Planning | FY23, FY24, and FY25 budgets account for project costs with knowledge $57,900 is refundable upon return of Army ABCS equipment | SOW, Congress | Budget requests must be approved by JRTC Commander and incorporated into DoD total budget approved by US Congress | Monthly |  |  |  | CPT G | 2023-10-29
6 | Assumption | CALL and CAL personnel are readily available for doctrine screening | Not Verified Yet | Doctrine Publication | CALL and CAL editors need to be scheduled for availability to streamline doctrine publication | AR 25-50 | CALL and CAL personnel proofread and edit doctrine submissions | Monthly |  |  |  | CPT G | 2023-10-29
7 | Assumption | Suite of ABCS systems integrate without issue | Not Verified Yet | Technology | The full suite of ABCS requires subject matter expert troubleshooting if issues with integration arise | CECOM, MCCOE | Military Liaison identifies the Mission Command Digital Master Gunners | Monthly |  |  |  | CPT G | 2023-10-29
8 | Assumption | Subcontracted portions of project are completed on schedule | Not Verified Yet | Planning | Subcontractor and Project Team Member contracts specify suspense dates or periods | SOW, Milestone Chart | Delay in contracted deliverables will delay overall schedule of project | Monthly |  |  |  | CPT G | 2023-10-29
9 | Assumption | Personnel turnover is mitigated by continuity of project team | Not Verified Yet | Administrative Coordination | Army and DoD personnel changeover due to Permanent Change of Station (PCS) or Federal Contracts outside the scope of this project will occur resulting in a lack of expertise | SOW | Project Team Members will act as Project Continuity subject matter experts and in-brief new Army and DoD personnel utilizing Knowledge Management Resources | Monthly |  |  |  | CPT G | 2023-10-29
10 | Assumption | Scope agreement remains without creep of requirements | Not Verified Yet | Planning | Agreed upon Scope statement revisions must be processed through the appropriate Scope change request channel and appoval authority | SOW | Stakeholder meetings and touchpoints will ensure Scope Statement compliance | Monthly |  |  |  | CPT G | 2023-10-29
11 | Assumption | Knowledge Management and software licenses are streamlined | Verified As Correct | Technology | Software licenses and cloud data storage must conform with Army IT and User Acceptable Policy | SOW, UAP, NEC | Knowledge Manager will confirm Army and DoD requirements through Network Enterprise Center | Monthly |  |  |  | CPT G | 2023-10-29
12 | Assumption | Price of materials remains within 3% variance of today's prices | Not Verified Yet | Material Acquisition | FY23, FY24, and FY25 budgets account for project costs with a 3% variance incorporated to account for product price increase each year | GCSS-A | Budget requests must be approved by JRTC Commander and incorporated into DoD total budget approved by US Congress | Monthly |  |  |  | CPT G | 2023-10-29
13 | Assumption | ABCS Army Equipment will be readily available for loan over duration of project | Verification In Process | Administrative Coordination | The full suite of ABCS Army Equipment to provide the Commander's Operations Picture (COP) will be temporarily purchased from 3/10th MTN BDE | SOW, Milestone Chart | Full suite of ABCS required for capablity performance measure and EM signature | Monthly |  |  |  | CPT G | 2023-10-29
14 | Assumption | ABCS Army Equipment maintenance contracts are still in place | Verified As Correct | Administrative Coordination | The full suite of ABCS Army Equipment requires maintenance and Subject Matter Expert troubleshooting from CECOM and the FSR program | GCSS-A, CECOM | JRTC has LAR and FSR support throughout the Fiscal Year | Monthly |  |  |  | CPT G | 2023-10-29
15 | Assumption | COVID-19 will not hinder project schedule | Not Verified Yet | Planning | COVID-19 restrictions will hinder project completion dramatically | CDC | This project cannot be completed remotely, another Black Swan event such as COVID-19 will require timeline and requirement adjustments | Monthly |  |  |  | CPT G | 2023-10-29
16 | Assumption | Project Team Members will be in position for duration of project | Not Verified Yet | Planning | Project Team Member Contracts will specify duration of project timeline and Non-Disclosure Agreements | SOW | Contracts attempt to reduce personnel turnover delays | Monthly |  |  |  | CPT G | 2023-10-29
17 | Assumption | Final products will be approved | Not Verified Yet | Approval | Chain of Command must be utilized for change requests, touchpoint approval, and final approval | SOW, CoC, FORSCOM | Military structure requires commander approval | Monthly |  |  |  | CPT G | 2023-10-29
18 | Assumption | Laptops, phones, printers, projectors, etc remain in good condition | Not Verified Yet | Technology | OS versions and patched software must conform with Army IT and User Acceptable Policy | SOW, Communications Plan, NEC | Knowledge Manager will confirm Army and DoD requirements through Network Enterprise Center | Monthly |  |  |  | CPT G | 2023-10-29
19 | Assumption | Incliment weather will not cause unmanageable schedule delays | Not Verified Yet | Planning | Incliment weather for long durations will hinder project completion dramatically | NWS, NOAA | This project cannot be completed remotely, severe incliment weather will require timeline and requirement adjustments | Monthly |  |  |  | CPT G | 2023-10-29
20 | Assumption | Project Benefits will fulfill expectations | Not Verified Yet | Approval | Project Benefit analysis produced deliverable products that must fulfill outlined expectations for project success | Benefit Register, SOW | Details and specificity in deliverables will reduce chance of unclear expectations | Monthly |  |  |  | CPT G | 2023-10-29
21 | Assumption | Team Member health and safety | Not Verified Yet | Planning | Lack of injury and illness will ensure timeliness of project completion | CDC, OSHA | Project Team Members being injured or falling ill can delay project schedule | Monthly |  |  |  | CPT G | 2023-10-29
22 | Assumption | Project classification remains Unclassified | Not Verified Yet | Planning | Overall classification of LSCO MCP Project will remain Unclassified | CUI | Increase in classification level will require further background checks, clearances, and additional equipment and permissions | Monthly |  |  |  | CPT G | 2023-10-29
23 | Assumption | Geopolitical climate will not accelarate project completion date | Not Verified Yet | Planning | The US Military is not currently engaged in a LSCO conflict, change in this status could accelarate expecations for deliverables required | Foreign Policy | If US Military engaes in LSCO operations, the LSCO MCP design will need to be ready ASAP | Monthly |  |  |  | CPT G | 2023-10-29
24 | Assumption | Training is available and adequate | Not Verified Yet | Administrative Coordination | This project incoroporates joint operations where personnel require training to fulfill their portion of the project | TRADOC | Military Liaison has critical role in Project Team LSCO education | Monthly |  |  |  | CPT G | 2023-10-29
25 | Assumption | ABCS Components capabilities are scalable | Verification In Process | Technology | ABCS components regularly require firmware and software updates; the capabilities need to be scalable for emerging LSCO requirements | CECOM, MCCOE | Technology firmware and software revisions need to be readily available for project compliance | Monthly |  |  |  | CPT G | 2023-10-29
26 | Assumption | Adversaries unable to exploit published results | Not Verified Yet | Planning | The US Military is not currently engaged in a LSCO conflict, change in this status could accelarate expecations for deliverables required | CUI, Foreign Policy | If US Military engaes in LSCO operations, the LSCO MCP design will need to be ready ASAP | Monthly |  |  |  | CPT G | 2023-10-29
27 | Constraint | Published timeline with milestone suspense dates | Verified As Correct | Planning | Schedule with milestone suspense dates deliverables must be completed | SOW, Milestone Chart | Schedule compliance | Monthly |  |  |  | CPT G | 2023-10-29
28 | Constraint | Approved budget covers projected and unforeseen costs | Not Verified Yet | Planning | FY23, FY24, and FY25 budgets account for project costs with knowledge $57,900 is refundable upon return of Army ABCS equipment | SOW, Congress | Budget requests must be approved by JRTC Commander and incorporated into DoD total budget approved by US Congress | Monthly |  |  |  | CPT G | 2023-10-29
29 | Constraint | Scope requirements must be met | Verified As Correct | Data Collection | Scope statement requirements and deliverables must be completed to expectation of quality for successful project completion | SOW, CoC, FORSCOM | Project expectation fulfillment required for successsful completion | Monthly |  |  |  | CPT G | 2023-10-29
30 | Constraint | Quality of working prototype and final product design | Not Verified Yet | Product Refinement | Stakeholders, FORSCOM, and Chain of Command have approval authority on product design | SOW | Military structure requires commander approval | Monthly |  |  |  | CPT G | 2023-10-29
31 | Constraint | LSCO requirement comprehension due dilligence | Verified As Correct | Planning | For the Project Team to have a full understanding of the scope requirements and deliverables, a week long familiarization course on LSCO and Lessons Learned in the Russo-Ukraine Conflict will be taught | SOW, TRADOC | Military Liaison has critical role in Project Team LSCO education | Monthly |  |  |  | CPT G | 2023-10-29
32 | Constraint | Contracted team member number | Not Verified Yet | Planning | The number of personnel approved to work on the Project Team cannot change | SOW, WBS | Budget considerations will not allow for additional personnel | Monthly |  |  |  | CPT G | 2023-10-29
33 | Constraint | Army Regulations | Verified As Correct | Stakeholder | Army Regulations must be understood and adhered to for smooth incorporation of final design into total force | Army Publishing Directorate houses all Army Regulations and Publications digitally | Military Liaison has critical role in Regulation adherance | Monthly |  |  |  | CPT G | 2023-10-29
34 | Constraint | State and Federal Legal Restrictions | Verified As Correct | Stakeholder | Staff Judge Advocate Legal Representative must review products prior to publication to ensure compliance with Local, State, Federal, and UCMJ Laws, Regulations, and Policies | UCMJ | Project and completed products require review by Staff Judge Advocate Legal Representative | Monthly |  |  |  | CPT G | 2023-10-29
35 | Constraint | Material storage space | Verification In Process | Administrative Coordination | Storage space for materials, tools, and prototype designs with protection from water is required | IMCOM | Rain, Snow, and Water will destroy prototypes and prototype materials | Monthly |  |  |  | CPT G | 2023-10-29
36 | Constraint | Construction space | Verification In Process | Administrative Coordination | Construction space for prototype fabrication with protection from water and electrical outlets is required | IMCOM | Rain, Snow, and Water will destroy prototypes and prototype materials; electrical outlets are required for power tools | Monthly |  |  |  | CPT G | 2023-10-29
37 | Constraint | Procurement through Army supply channels | Verified As Correct | Material Acquisition | Utulizing the Army's class of supply system, GCSS-A, materials are procured and delivered on schedule | GCSS-A | Administrators require GCSS-A access and SLOC of local SSA | Monthly |  |  |  | CPT G | 2023-10-29
38 | Constraint | Knowledge Management and software licenses through Army | Verified As Correct | Technology | Software licenses and cloud data storage must conform with Army IT and User Acceptable Policy | NEC, UAP, Communications Plan | Knowledge Manager will confirm Army and DoD requirements through Network Enterprise Center | Monthly |  |  |  | CPT G | 2023-10-29
39 | Constraint | Chain of Command Approval | Verified As Correct | Approval | Chain of Command must be utilized for change requests, touchpoint approval, and final approval | SOW | Military structure requires commander approval | Monthly |  |  |  | CPT G | 2023-10-29

## Ranges
Type | Status | Category
Assumption | Not Verified Yet | Planning
Constraint | Verification In Process | Design
| Verified As Correct | Construction
| Verified As Incorrect | Administrative Coordination
Material Acquisition
Stakeholder
Approval
Data Collection
Product Refinement
Doctrine Publication
Technology