## Stakeholders
Stakeholder Management Plan
Project Name: LSCO MCP |  |  |  |  | Project Manager: CPT G |  |  | Date: 10NOV23
Who | What |  |  |  | How |  | Who | When | Other
Stakeholder | Stakeholder's Role | Influence High/Low | Interest High/Low | Support Neutral Against | Monitor Inform Satisfy Manage | Strategy | Strategy Owner | Strategy Date | Comments
Designers | Key | High | High | Support | Manage | Team member, regular interaction
Administrators | Key | Low | High | Support | Inform | Team member, regular interaction
Contractor | Key | High | High | Support | Manage | Team member, regular interaction
Military Liaison | Key | High | High | Support | Manage | Team member, regular interaction
Photographer | Secondary | Low | High | Support | Monitor | Team member, regular interaction
Logistician | Key | Low | High | Support | Monitor | Team member, regular interaction
Knowledge Manager | Key | Low | High | Support | Monitor | Team member, regular interaction
Pilot | Secondary | Low | High | Neutral | Monitor | Team member, regular interaction
Electromagnetic Analyzer | Secondary | Low | High | Neutral | Monitor | Team member, regular interaction
Writer | Secondary | Low | High | Neutral | Monitor | Team member, regular interaction
Editor | Secondary | Low | High | Neutral | Monitor | Team member, regular interaction
Project Manager | Key | High | High | Support | Manage | Team member, regular interaction
Distinguished Visitors | Key | High | High | Support | Manage | VIP, regular and personal interaction
Vehicle Mechanic | Secondary | Low | Low | Neutral | Monitor | Service, Administrators manage
Railyard Workers | Secondary | Low | Low | Neutral | Monitor | Service, Administrators manage
ABCS Integration Specialist | Secondary | Low | Low | Support | Inform | Service, Administrators and Military Liaison manage
Legal | Secondary | High | Low | Neutral | Inform | Service, Administrators and Military Liaison manage
Office Landlord | Secondary | Low | Low | Neutral | Monitor | Service, Administrators manage
Utility Companies | Secondary | Low | Low | Neutral | Monitor | Service, Administrators manage
Satellite Team | Secondary | Low | Low | Neutral | Monitor | Service, Administrators and Military Liaison manage
GCSS-A Suppliers | Secondary | Low | Low | Neutral | Monitor | Service, Logistician and Military Liaison manage
Materials Deliverer | Secondary | Low | Low | Neutral | Monitor | Service, Logistician and Military Liaison manage
Bulk Fuel Deliverer | Secondary | Low | Low | Neutral | Monitor | Service, Logistician and Military Liaison manage
Conference Hall Manager | Secondary | Low | Low | Neutral | Monitor | Service, Administrators manage
Conference Hall Staff | Secondary | Low | Low | Neutral | Monitor | Service, Administrators manage
COMSEC Custodian | Secondary | Low | Low | Neutral | Monitor | Service, Knowledge Manager and Military Liaison manage
ABCS Systems Troubleshooting SME | Secondary | Low | Low | Support | Inform | Service, Knowledge Manager and Military Liaison manage
Environmental Compliance Officer | Secondary | Low | Low | Neutral | Monitor | Service, Administrators and Military Liaison manage
Safety Regulation Compliance Officer | Secondary | Low | Low | Neutral | Monitor | Service, Administrators and Military Liaison manage
Security Background Adjudicator | Secondary | Low | Low | Neutral | Monitor | Service, Administrators and Military Liaison manage
LSCO Warfighting Researchers | Key | Low | Low | Support | Inform | Service, Administrators and Military Liaison manage
Communications and Electronics Shop Manager | Secondary | Low | Low | Neutral | Monitor | Service, Knowledge Manager and Military Liaison manage
Communications and Electronics Shop Staff | Secondary | Low | Low | Neutral | Monitor | Service, Knowledge Manager and Military Liaison manage
2IBCT/82D ABN DIV Command and Staff | Primary | Low | High | Support | Inform | Impacted Organizations, Knowledge Manager and Military Liaison and Admistrators manage
3IBCT/25TH IN DIV Command and Staff | Primary | Low | High | Support | Inform | Impacted Organizations, Knowledge Manager and Military Liaison and Admistrators manage
75TH RANGER REG Command and Staff | Primary | Low | High | Support | Inform | Impacted Organizations, Knowledge Manager and Military Liaison and Admistrators manage
2IBCT/101ST ABN DIV Command and Staff | Primary | Low | High | Support | Inform | Impacted Organizations, Knowledge Manager and Military Liaison and Admistrators manage
1IBCT/11TH ABN DIV Command and Staff | Primary | Low | High | Support | Inform | Impacted Organizations, Knowledge Manager and Military Liaison and Admistrators manage
1IBCT/82D ABN DIV Command and Staff | Primary | Low | High | Support | Inform | Impacted Organizations, Knowledge Manager and Military Liaison and Admistrators manage
7TH SF GROUP Command and Staff | Primary | Low | High | Support | Inform | Impacted Organizations, Knowledge Manager and Military Liaison and Admistrators manage
1IBCT/10TH MTN DIV Command and Staff | Primary | Low | High | Support | Inform | Impacted Organizations, Knowledge Manager and Military Liaison and Admistrators manage
JRTC Command and Staff | Key | High | High | Support | Manage | VIP, regular and personal interaction
FORSCOM Command and Staff | Key | High | High | Support | Manage | VIP, monitor through chain-of-command
Center for Army Lessons Learned | Secondary | Low | High | Support | Inform | Publication, Knowledge Manager and Military Liaison and Admistrators manage
TRADOC Command and Staff | Secondary | Low | High | Support | Inform | VIP, monitor through chain-of-command
Army Times | Secondary | Low | Low | Neutral | Monitor | Publication, Knowledge Manager and Military Liaison and Admistrators manage
Secretary of the Army | Key | High | Low | Support | Manage | VIP, monitor through chain-of-command
Joint Chiefs of Staff | Key | High | Low | Support | Manage | VIP, monitor through chain-of-command
Secretary of Defense | Key | High | Low | Support | Satisfy | VIP, monitor through chain-of-command
US Congress | Key | High | Low | Support | Satisfy | VIP, monitor through chain-of-command
US Senate | Key | High | Low | Support | Satisfy | VIP, monitor through chain-of-command
US President | Key | High | Low | Support | Satisfy | VIP, monitor through chain-of-command
Congress Appropriations Committee | Key | High | Low | Support | Satisfy | VIP, monitor through chain-of-command
Congress Armed Services Committee | Key | High | Low | Support | Satisfy | VIP, monitor through chain-of-command
Congress Budget Committee | Key | High | Low | Support | Satisfy | VIP, monitor through chain-of-command
Congress Veterans Affairs Committee | Key | High | Low | Support | Satisfy | VIP, monitor through chain-of-command
Mission Command Center of Excellence | Primary | High | High | Support | Manage | Educational Organizations, Knowledge Manager and Military Liaison and Admistrators manage
Manuever Center of Excellence | Primary | High | High | Support | Manage | Educational Organizations, Knowledge Manager and Military Liaison and Admistrators manage
Cyber Center of Excellence | Secondary | High | Low | Support | Manage | Educational Organizations, Knowledge Manager and Military Liaison and Admistrators manage
Fires Center of Excellence | Primary | High | High | Support | Manage | Educational Organizations, Knowledge Manager and Military Liaison and Admistrators manage
Intelligence Center of Excellence | Primary | High | High | Support | Manage | Educational Organizations, Knowledge Manager and Military Liaison and Admistrators manage
Manuever Support Center of Excellence | Primary | High | High | Support | Manage | Educational Organizations, Knowledge Manager and Military Liaison and Admistrators manage
Medical Department Center of Excellence | Secondary | High | Low | Support | Manage | Educational Organizations, Knowledge Manager and Military Liaison and Admistrators manage
Sustainment Center of Excellence | Secondary | High | Low | Support | Manage | Educational Organizations, Knowledge Manager and Military Liaison and Admistrators manage
US Taxpayers | Secondary | Low | Low | Neutral | Monitor | Budget, Adminstrators manage
Combined Arms Center | Secondary | Low | Low | Support | Monitor | Publication, Knowledge Manager and Military Liaison and Admistrators manage
Security Specialist | Secondary | Low | Low | Neutral | Monitor | Service, Administrators manage
Account Manager | Secondary | Low | Low | Neutral | Monitor | Service, Administrators manage
Practical Application Analyst | Key | Low | High | Support | Manage | Service, Administrators manage
Chief Information Officer | Key | High | High | Support | Manage | VIP, monitor through chain-of-command
Chief Operations Officer | Key | High | High | Support | Manage | VIP, monitor through chain-of-command
Chief Fires Officer | Key | High | High | Support | Manage | VIP, monitor through chain-of-command
Chief Intelligence Officer | Key | High | High | Support | Manage | VIP, monitor through chain-of-command
Contract Manager | Secondary | Low | Low | Neutral | Monitor | Service, Administrators manage
Support Specialist | Secondary | Low | Low | Neutral | Monitor | Service, Administrators manage
Supply Specialist | Secondary | Low | Low | Neutral | Monitor | Service, Logistician and Military Liaison manage
Test Manager | Key | Low | High | Neutral | Manage | VIP, regular and personal interaction
Technical Writer | Secondary | Low | High | Neutral | Monitor | Service, Administrators manage
Steering Committee | Key | High | High | Support | Manage | VIP, regular and personal interaction
End Users | Primary | High | High | Support | Inform | Impacted Users, Knowledge Manager and Military Liaison and Admistrators manage
Government Regulators | Secondary | High | Low | Neutral | Inform | VIP, monitor through Military Liaison
DoD Vendors | Primary | High | Low | Support | Satisfy | VIP, monitor through Military Liaison
Main Stream Media | Secondary | High | Low | Neutral | Monitor | Publication, Knowledge Manager and Military Liaison and Admistrators manage
Social Media | Secondary | High | Low | Neutral | Monitor | Publication, Knowledge Manager and Military Liaison and Admistrators manage
Military Social Media Influencers | Secondary | High | Low | Neutral | Monitor | Publication, Knowledge Manager and Military Liaison and Admistrators manage
Foreign Militariy Partners | Secondary | Low | High | Support | Monitor | VIP, monitor through chain-of-command
NATO | Secondary | Low | High | Support | Satisfy | VIP, monitor through chain-of-command
Foreign Military Adversaries | Primary | Low | High | Against | Inform | VIP, monitor through Military Liaison
Foreign Main Stream Media | Secondary | Low | Low | Neutral | Monitor | Publication, Knowledge Manager and Military Liaison and Admistrators manage
Infantry Instructors | Primary | Low | Low | Support | Inform | Impacted Educators, Knowledge Manager and Military Liaison and Admistrators manage
Military Times | Secondary | Low | Low | Neutral | Monitor | Publication, Knowledge Manager and Military Liaison and Admistrators manage
Marine Corps | Secondary | Low | Low | Support | Monitor | Military Branch, Knowledge Manager and Military Liaison and Admistrators manage
Air Force | Secondary | Low | Low | Support | Monitor | Military Branch, Knowledge Manager and Military Liaison and Admistrators manage
Navy | Secondary | Low | Low | Neutral | Monitor | Military Branch, Knowledge Manager and Military Liaison and Admistrators manage
Space Force | Secondary | Low | Low | Neutral | Monitor | Military Branch, Knowledge Manager and Military Liaison and Admistrators manage
CIA | Secondary | Low | Low | Support | Monitor | Government Organization, Knowledge Manager and Military Liaison and Admistrators manage
Paramilitary Contracting Companies | Secondary | Low | Low | Support | Monitor | Private Company, Knowledge Manager and Military Liaison and Admistrators manage
Federal Reserve | Secondary | Low | Low | Neutral | Monitor | Budget, Adminstrators manage
Subject Matter Experts | Key | High | High | Support | Manage | VIP, regular and personal interaction
Stakeholder: Enter the names of the project stakeholders
Stakeholder's Role: Enter the stakeholders role in the project
Influence High/Low: Use the dropdown box to enter the stakeholders level of influence in the project (Select High or Low)
Interest High/Low: Use the dropdown box to enter the stakeholders level of interest in the project (Select High or Low)
Monitor, Inform, Satisfy or Manage: Use the dropdown box to select an approach for the stakeholder based on their level of influence and level of interest: - High influence/High interest: Manage by fully engaging them in the process - High influence/Low interest: Satisfy with levels of communication necessary to meet their needs - Low influence/Low interest: Monitor for changing needs and interests - Low influence/High interest: Inform with appropriate levels of communication to safeguard against issues
Strategy: Enter a strategy action based on the selection of monitor, inform, satisfy, or manage
Strategy Owner: Enter a strategy action owner
Strategy Date: Enter a strategy action date
Comments: Enter necessary comments based on the stakeholder line item
Note on G5: High influence/High interest: Manage by fully engaging them in the process High influence/Low interest: Satisfy with levels of communication necessary to meet their needs Low influence/Low interest: Monitor for changing needs and interests Low influence/High interest: Inform with appropriate levels of communication to safeguard against issues